## Cover
[ORGANIZATION NAME]
00 — Master PMO Documentation Framework
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Governance, Scope, Schedule, Finance, Stakeholders, Resources, Risk
Project ID | PRJ-2026-001 |  | Focus area(s) | Initiating, Planning, Executing, Monitoring & Controlling, Closing
Document ID | PRJ-2026-001-MDF |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | Master PMO Documentation Framework |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | PMO Lead
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. The Document Register defines, for all 25 artefacts, whether each is Mandatory (M), Conditional (C) or Optional (O) by project complexity, when it is created, who owns and approves it, when it is baselined and which artefacts it feeds.
2. Use the Gate Checklist at each governance gate: an artefact marked M for your complexity level must be at the stated status before the gate can pass.
3. Delegated authority, escalation and RAG thresholds here are the PMO defaults; record project-specific tailoring in the Integrated PMP (doc 02).
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## Document Register
00 — Master PMO Documentation Framework ¦ Document Register
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
# | Artefact | Document ID | Format | Primary performance domain | Focus area(s) | Low | Medium | High | Condition / tailoring note | Control category | Created in | Trigger | Owner | Approver | Consulted | Baselined | Update cadence | Feeds (outputs to) | Fed by (inputs from) | Objective acceptance criteria
01 | Project Charter | PRJ-2026-001-CHR | docx | Governance | Initiating | M | M | M |  | Authorizing document | Initiating (G1) | Approved business case / project request | Project Manager | Project Sponsor | PMO, Finance, key stakeholders | Approved at G1 (v1.0) | Revisit at each gate; change only via CR | 02, 03, 04, 06, 08, 10, 13, 15, 18, 25 | Business case / project request | • Signed by the Project Sponsor (G1 record) • Every objective is SMART with metric, target and measurement source • In-scope and out-of-scope items each listed explicitly • Summary budget states estimate class and accuracy range • PM authority and tolerances quantified (budget, schedule, staffing)
02 | Integrated Project Management Plan | PRJ-2026-001-PMP | docx | Governance | Planning, Monitoring & Controlling | M | M | M |  | Controlled management plan | Planning (G2) | Charter approved | Project Manager | Project Sponsor / Steering Committee | Workstream leads, PMO, Finance | v1.0 at G2 — integrates all baselines | Review at each gate; update via change control | 12, 19, 20, 21, 22, 23, 24, 25 | 01, 03, 06, 08, 11, 12, 13, 14, 15, 17, 18 | • Every subsidiary plan and baseline listed with Document ID and version • Tailoring decision recorded for each of the 7 performance domains • Change-authority thresholds stated in time and money • RAG thresholds quantified for schedule, cost, scope, risk and quality • Gates G1–G5 defined with approver and exit criteria
03 | Scope Management Plan | PRJ-2026-001-SCP | docx | Scope | Planning | C | M | M | Low complexity: may be a section of the Integrated PMP (02). | Controlled management plan | Planning (G2) | Charter approved | Project Manager | Project Sponsor | Business Owner, Business Analyst | Scope statement baselined at G2 (scope baseline) | Review at each gate | 02, 04, 05, 17 | 01 | • Scope statement includes deliverables, acceptance criteria, exclusions, constraints and assumptions • WBS rules defined (100% rule, numbering, work-package size) • Deliverable acceptance procedure names acceptor and review period • Scope variance threshold defined
04 | Requirements & RTM | PRJ-2026-001-RTM | xlsx | Scope | Planning, Monitoring & Controlling | C | M | M | Low complexity: a requirements list in the Charter may suffice. | Living register / log | Planning (G2) | Scope Management Plan drafted | Business Analyst | Business Owner | Stakeholders, QA Lead, Technical Lead | Requirements baseline approved at G2; changes via CR | Weekly during analysis/build; at each test cycle | 05, 17, 22, 25 | 01, 03, 10 | • 100% of requirements uniquely identified with a source • 100% of 'Must' requirements have testable acceptance criteria • Traceability ≥ 95% (WBS, deliverable, test) by G3; 100% verified by G4 • Status of each requirement current at each gate
05 | WBS & WBS Dictionary | PRJ-2026-001-WBS | xlsx | Scope | Planning | M | M | M |  | Baseline component | Planning (G2) | Scope statement and requirements approved | Project Manager | Project Sponsor | Workstream leads | Scope baseline at G2 (with 03 scope statement) | Change only via approved CR | 07, 09, 13, 14, 16 | 03, 04 | • 100% rule satisfied: all and only the project scope • Every work package has one accountable owner and a dictionary entry • Work packages sized to 8–80 h or one reporting period • Each work package mapped to a control account
06 | Schedule Management Plan | PRJ-2026-001-SMP | docx | Schedule | Planning | C | M | M | Low complexity: may be a section of the Integrated PMP (02). | Controlled management plan | Planning (G2) | Charter approved | Project Manager | Project Sponsor | PMO / scheduler | Approved at G2 with the PMP | Review at each gate | 02, 07, 22 | 01 | • Scheduling method, tool, calendar and units stated • Progress-measurement rules defined (0/100, 50/50, weighted) • Schedule variance thresholds quantified (days and SPI) • Re-baselining rule tied to change control
07 | Master Schedule | PRJ-2026-001-MSC | xlsx | Schedule | Planning, Monitoring & Controlling | M | M | M |  | Baseline component | Planning (G2) | WBS approved | Project Manager | Project Sponsor | Work package owners | Schedule baseline at G2 | Status updated weekly; baseline changed only via CR | 09, 13, 22, 25 | 05, 06, 13, 16, 18 | • Every activity linked to a WBS ID • No open ends: every activity has a predecessor and a successor (except start/finish) • Gate milestones G1–G5 present with zero duration • Baseline dates captured and frozen at G2
08 | Financial Management Plan | PRJ-2026-001-FMP | docx | Finance | Planning | C | M | M | Low complexity: may be a section of the Integrated PMP (02). | Controlled management plan | Planning (G2) | Charter approved | Project Manager | Project Sponsor | Finance Business Partner | Approved at G2 with the PMP | Review quarterly and at each gate | 02, 09, 18, 22 | 01, 15 | • Estimate classes and accuracy ranges defined • Contingency and management reserve basis and release authority defined • Spending authority stated per role with monetary limits • EVM formulas and reporting cadence stated
09 | Project Budget | PRJ-2026-001-BUD | xlsx | Finance | Planning, Monitoring & Controlling | M | M | M |  | Baseline component | Planning (G2) | WBS and schedule drafted | Project Manager | Project Sponsor | Finance, Procurement | Cost baseline at G2 (excl. management reserve) | Actuals monthly; baseline changed only via CR | 22, 25 | 05, 07, 08, 13, 15, 16, 18 | • Bottom-up estimate by work package; sum equals cost baseline • Contingency traceable to Risk Register EMV • Time-phased Planned Value equals the cost baseline • CPI, SPI and EAC reported each month
10 | Stakeholder Register | PRJ-2026-001-SHR | xlsx | Stakeholders | Initiating, Planning | M | M | M |  | Living register / log | Initiating (G1) | Project request received | Project Manager | Project Manager | Sponsor, Business Owner | Not baselined — snapshot at each gate | Monthly and on organizational change | 04, 11, 12, 14, 16 | 01 | • Every stakeholder scored for power and interest • Current and desired engagement recorded for all key stakeholders • Each key stakeholder has a relationship owner • Register reviewed at each gate
11 | Stakeholder Engagement Plan | PRJ-2026-001-SEP | docx | Stakeholders | Planning, Executing | O | C | M | Mandatory when the project spans more than one organization or drives significant organizational change. | Controlled management plan | Planning (G2) | Stakeholder Register established | Project Manager | Project Sponsor | Change lead, Business Owner | Approved at G2 with the PMP | Monthly engagement review | 02, 12, 22 | 10 | • Engagement gap and action defined for every key stakeholder • Each action has an owner, date and success indicator • Engagement metrics have targets (e.g. ≥ 80% at desired level)
12 | Communication Plan | PRJ-2026-001-COM | xlsx | Stakeholders | Planning, Executing | M | M | M |  | Controlled management plan | Planning (G2) | Stakeholder Register established | Project Manager | Project Manager | Sponsor, Change lead | Approved at G2; maintained as a living plan | Review monthly | 02, 22 | 02, 10, 11, 14 | • Every governance forum and report has audience, owner, frequency and channel • Escalation path matches the Integrated PMP • Status report cadence and distribution defined
13 | Resource Management Plan | PRJ-2026-001-RMP | docx | Resources | Planning, Executing | O | C | M | Mandatory when the team exceeds ~10 people, uses contracted staff, or shares scarce resources. | Controlled management plan | Planning (G2) | WBS drafted | Project Manager | Project Sponsor | Functional managers, HR | Approved at G2 with the PMP | Review at each gate | 02, 07, 09, 14 | 01, 05, 07, 14 | • Every role has responsibilities, authority and competencies • Acquisition source and dates defined for each role • Physical resources listed with source and dates • Release and handover procedure defined
14 | RACI Matrix | PRJ-2026-001-RACI | xlsx | Resources | Planning | C | M | M | Low complexity: responsibilities may be shown in the Charter role table. | Living register / log | Planning (G2) | WBS and roles defined | Project Manager | Project Manager | All role holders | Approved at G2; maintained as roles change | Review at each gate | 02, 12, 13 | 05, 10, 13 | • Exactly one 'A' per row • At least one 'R' per row • Every level-2 WBS element and governance deliverable covered
15 | Risk Management Plan | PRJ-2026-001-RKP | docx | Risk | Planning | C | M | M | Low complexity: risk approach may be a section of the Integrated PMP (02). | Controlled management plan | Planning (G2) | Charter approved | Project Manager | Project Sponsor | Team, PMO | Approved at G2 with the PMP | Review at each gate | 02, 08, 09, 16 | 01 | • Probability and impact scales defined (1–5) with objective criteria • 5×5 matrix bands and required action per band defined • Risk appetite and escalation thresholds quantified • Contingency derivation method stated
16 | Risk Register + 5×5 Matrix | PRJ-2026-001-RKR | xlsx | Risk | Planning, Executing, Monitoring & Controlling | M | M | M |  | Living register / log | Planning (G2) | Risk Management Plan drafted | Project Manager | Project Manager (escalated risks: Sponsor) | Risk owners | Risk profile snapshot at G2 sets contingency | Weekly review of High/Critical; full review monthly | 07, 09, 19, 22, 23, 24 | 05, 10, 15, 18 | • Each risk written as cause → event → effect • Every High/Critical risk has an owner, response and due date • Residual score recorded after response • EMV totals reconcile to contingency reserve
17 | Quality Management Plan | PRJ-2026-001-QMP | docx | Scope | Planning, Executing | O | C | M | Mandatory when regulated, safety-critical, or when contractual quality standards apply. | Controlled management plan | Planning (G2) | Requirements and scope defined | QA Lead | Project Sponsor | Business Owner, Technical Lead | Approved at G2 with the PMP | Review at each gate and after audits | 02, 24, 25 | 03, 04 | • Each quality objective has metric, target and measurement method • QA audits and QC activities scheduled • Non-conformance severity and corrective-action process defined
18 | Procurement Plan | PRJ-2026-001-PRC | docx | Resources | Planning, Executing | C | C | M | Mandatory whenever goods or services are acquired from external suppliers. | Controlled management plan | Planning (G2) | Make-or-buy decision | Project Manager | Project Sponsor / Procurement Lead | Procurement, Legal, Finance | Approved at G2 with the PMP | Review per procurement event | 02, 07, 09, 16 | 01, 08 | • Make-or-buy decision documented for each item • Contract type and procurement method justified • Weighted source-selection criteria total 100% • Vendor performance KPIs defined
19 | RAID Log | PRJ-2026-001-RAID | xlsx | Risk | Executing, Monitoring & Controlling | M | M | M |  | Living register / log | Executing (G2) | Plans baselined | Project Manager | Project Manager | Team, owners | Not baselined — snapshot at each gate | Weekly team review | 20, 22, 23, 24 | 02, 16 | • Every open item has an owner and target date • Issues escalated per level within stated response times • No issue older than 30 days without a review entry
20 | Change Request | PRJ-2026-001-CR | docx | Governance | Monitoring & Controlling | M | M | M |  | Control form / record | Monitoring & Controlling (G2) | Any proposed change to a baseline or controlled document | Requestor / Project Manager | PM, CCB or Steering Committee per threshold | Affected owners | Each instance filed; approved CRs re-baseline affected artefacts | Per change | 21, 23 | 02, 19 | • Impact quantified for scope, schedule (days) and cost • Options and recommendation recorded • Decision authority matches the threshold in the Integrated PMP • Documents to re-version listed
21 | Change Log | PRJ-2026-001-CHL | xlsx | Governance | Monitoring & Controlling | M | M | M |  | Living register / log | Monitoring & Controlling (G2) | First change request | Project Manager | Project Manager | CCB | Not baselined | Updated per change; reviewed at each CCB | 22, 25 | 02, 20 | • Every CR logged within 2 business days • Approved impacts reconcile to baseline revisions • Decision date and authority recorded for all closed CRs
22 | Project Status Report | PRJ-2026-001-PSR | pptx | Governance | Monitoring & Controlling | M | M | M |  | Performance report | Monitoring & Controlling (G2) | End of each reporting period | Project Manager | Project Manager (distributed to Sponsor) | Workstream leads | Not baselined — numbered periodic issue | Bi-weekly or monthly per Communication Plan | 23, 24, 25 | 02, 04, 06, 07, 08, 09, 11, 12, 16, 19, 21 | • RAG status applies the Integrated PMP thresholds • SPI/CPI and milestone variance stated • All Critical risks and High issues reported • Decisions required named with owner and date
23 | Decision Log | PRJ-2026-001-DCL | xlsx | Governance | Executing, Monitoring & Controlling | C | M | M | Low complexity: decisions may be recorded in meeting minutes. | Living register / log | Executing (G2) | First governance decision | Project Manager | Project Manager | Decision makers | Not baselined | Per decision | 24, 25 | 02, 16, 19, 20, 22 | • Each decision records options, rationale and authority level • Related CR, risk or issue referenced • Decision communicated to named audience
24 | Lessons Learned Register | PRJ-2026-001-LLR | xlsx | Governance | Executing, Closing | M | M | M |  | Living register / log | Executing (G2) | Plans baselined | Project Manager | Project Manager | Team, stakeholders, PMO | Not baselined — final issue at G5 | At each gate and after significant events | 25 | 02, 16, 17, 19, 22, 23 | • Lessons captured at every gate, not only at closure • Each lesson tagged by focus area and performance domain • Each 'to improve' lesson has a recommendation and owner
25 | Project Closure Report | PRJ-2026-001-PCR | docx | Governance | Closing | M | M | M |  | Closing record | Closing (G5) | Final acceptance (G4) | Project Manager | Project Sponsor | Business Owner, Finance, PMO | Approved at G5; archived | Once | Organizational process assets | 01, 02, 04, 07, 09, 17, 21, 22, 23, 24 | • Each Charter objective reported as met / partly met / not met with evidence • Final cost and schedule variance against baselines stated • All outstanding items transferred to named owners • Administrative closure checklist complete

## Gate Checklist
00 — Master PMO Documentation Framework ¦ Governance Gate Checklist
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
G1 — Initiation gate
Focus area: Initiating • Approver: Project Sponsor
Exit criteria: Charter signed; Stakeholder Register established; PM appointed with delegated authority.
# | Artefact | Low | Med | High | Required status at gate | Approver | Done | Evidence / link
01 | Project Charter | M | M | M | Approved v1.0 | Project Sponsor | ☐
10 | Stakeholder Register | M | M | M | Established and current | Project Manager | ☐
G2 — Planning / baseline gate
Focus area: Planning • Approver: Steering Committee
Exit criteria: Integrated PMP v1.0 approved; scope, schedule and cost baselines approved; risk register populated; contingency set.
# | Artefact | Low | Med | High | Required status at gate | Approver | Done | Evidence / link
01 | Project Charter | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
02 | Integrated Project Management Plan | M | M | M | Approved v1.0 | Project Sponsor / Steering Committee | ☐
03 | Scope Management Plan | C | M | M | Approved v1.0 | Project Sponsor | ☐
04 | Requirements & RTM | C | M | M | Established and current | Business Owner | ☐
05 | WBS & WBS Dictionary | M | M | M | Approved v1.0 | Project Sponsor | ☐
06 | Schedule Management Plan | C | M | M | Approved v1.0 | Project Sponsor | ☐
07 | Master Schedule | M | M | M | Approved v1.0 | Project Sponsor | ☐
08 | Financial Management Plan | C | M | M | Approved v1.0 | Project Sponsor | ☐
09 | Project Budget | M | M | M | Approved v1.0 | Project Sponsor | ☐
10 | Stakeholder Register | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
11 | Stakeholder Engagement Plan | O | C | M | Approved v1.0 | Project Sponsor | ☐
12 | Communication Plan | M | M | M | Approved v1.0 | Project Manager | ☐
13 | Resource Management Plan | O | C | M | Approved v1.0 | Project Sponsor | ☐
14 | RACI Matrix | C | M | M | Established and current | Project Manager | ☐
15 | Risk Management Plan | C | M | M | Approved v1.0 | Project Sponsor | ☐
16 | Risk Register + 5×5 Matrix | M | M | M | Established and current | Project Manager (escalated risks: Sponsor) | ☐
17 | Quality Management Plan | O | C | M | Approved v1.0 | Project Sponsor | ☐
18 | Procurement Plan | C | C | M | Approved v1.0 | Project Sponsor / Procurement Lead | ☐
19 | RAID Log | M | M | M | Established and current | Project Manager | ☐
21 | Change Log | M | M | M | Established and current | Project Manager | ☐
22 | Project Status Report | M | M | M | Established and current | Project Manager (distributed to Sponsor) | ☐
23 | Decision Log | C | M | M | Established and current | Project Manager | ☐
24 | Lessons Learned Register | M | M | M | Established and current | Project Manager | ☐
G3 — Execution readiness / mid-point gate
Focus area: Executing • Approver: Steering Committee
Exit criteria: Deliverables built to plan; quality control evidence available; performance within tolerance or recovery plan approved.
# | Artefact | Low | Med | High | Required status at gate | Approver | Done | Evidence / link
01 | Project Charter | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
02 | Integrated Project Management Plan | M | M | M | Current approved version; changes via CR | Project Sponsor / Steering Committee | ☐
03 | Scope Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
04 | Requirements & RTM | C | M | M | Up to date; gate snapshot taken | Business Owner | ☐
05 | WBS & WBS Dictionary | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
06 | Schedule Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
07 | Master Schedule | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
08 | Financial Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
09 | Project Budget | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
10 | Stakeholder Register | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
11 | Stakeholder Engagement Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
12 | Communication Plan | M | M | M | Current approved version; changes via CR | Project Manager | ☐
13 | Resource Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
14 | RACI Matrix | C | M | M | Up to date; gate snapshot taken | Project Manager | ☐
15 | Risk Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
16 | Risk Register + 5×5 Matrix | M | M | M | Up to date; gate snapshot taken | Project Manager (escalated risks: Sponsor) | ☐
17 | Quality Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
18 | Procurement Plan | C | C | M | Current approved version; changes via CR | Project Sponsor / Procurement Lead | ☐
19 | RAID Log | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
21 | Change Log | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
22 | Project Status Report | M | M | M | Latest period issued | Project Manager (distributed to Sponsor) | ☐
23 | Decision Log | C | M | M | Up to date; gate snapshot taken | Project Manager | ☐
24 | Lessons Learned Register | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
G4 — Acceptance & transition gate
Focus area: Monitoring & Controlling • Approver: Sponsor / Business Owner
Exit criteria: All deliverables formally accepted against criteria; RTM fully verified; operational handover agreed.
# | Artefact | Low | Med | High | Required status at gate | Approver | Done | Evidence / link
01 | Project Charter | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
02 | Integrated Project Management Plan | M | M | M | Current approved version; changes via CR | Project Sponsor / Steering Committee | ☐
03 | Scope Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
04 | Requirements & RTM | C | M | M | Up to date; gate snapshot taken | Business Owner | ☐
05 | WBS & WBS Dictionary | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
06 | Schedule Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
07 | Master Schedule | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
08 | Financial Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
09 | Project Budget | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
10 | Stakeholder Register | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
11 | Stakeholder Engagement Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
12 | Communication Plan | M | M | M | Current approved version; changes via CR | Project Manager | ☐
13 | Resource Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
14 | RACI Matrix | C | M | M | Up to date; gate snapshot taken | Project Manager | ☐
15 | Risk Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
16 | Risk Register + 5×5 Matrix | M | M | M | Up to date; gate snapshot taken | Project Manager (escalated risks: Sponsor) | ☐
17 | Quality Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
18 | Procurement Plan | C | C | M | Current approved version; changes via CR | Project Sponsor / Procurement Lead | ☐
19 | RAID Log | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
21 | Change Log | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
22 | Project Status Report | M | M | M | Latest period issued | Project Manager (distributed to Sponsor) | ☐
23 | Decision Log | C | M | M | Up to date; gate snapshot taken | Project Manager | ☐
24 | Lessons Learned Register | M | M | M | Up to date; gate snapshot taken | Project Manager | ☐
G5 — Closure gate
Focus area: Closing • Approver: Project Sponsor
Exit criteria: Closure Report approved; contracts and finances closed; lessons learned submitted; records archived.
# | Artefact | Low | Med | High | Required status at gate | Approver | Done | Evidence / link
01 | Project Charter | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
02 | Integrated Project Management Plan | M | M | M | Current approved version; changes via CR | Project Sponsor / Steering Committee | ☐
03 | Scope Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
04 | Requirements & RTM | C | M | M | Final issue, archived | Business Owner | ☐
05 | WBS & WBS Dictionary | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
06 | Schedule Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
07 | Master Schedule | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
08 | Financial Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
09 | Project Budget | M | M | M | Current approved version; changes via CR | Project Sponsor | ☐
10 | Stakeholder Register | M | M | M | Final issue, archived | Project Manager | ☐
11 | Stakeholder Engagement Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
12 | Communication Plan | M | M | M | Current approved version; changes via CR | Project Manager | ☐
13 | Resource Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
14 | RACI Matrix | C | M | M | Final issue, archived | Project Manager | ☐
15 | Risk Management Plan | C | M | M | Current approved version; changes via CR | Project Sponsor | ☐
16 | Risk Register + 5×5 Matrix | M | M | M | Final issue, archived | Project Manager (escalated risks: Sponsor) | ☐
17 | Quality Management Plan | O | C | M | Current approved version; changes via CR | Project Sponsor | ☐
18 | Procurement Plan | C | C | M | Current approved version; changes via CR | Project Sponsor / Procurement Lead | ☐
19 | RAID Log | M | M | M | Final issue, archived | Project Manager | ☐
21 | Change Log | M | M | M | Final issue, archived | Project Manager | ☐
22 | Project Status Report | M | M | M | Latest period issued | Project Manager (distributed to Sponsor) | ☐
23 | Decision Log | C | M | M | Final issue, archived | Project Manager | ☐
24 | Lessons Learned Register | M | M | M | Final issue, archived | Project Manager | ☐
25 | Project Closure Report | M | M | M | Approved v1.0 | Project Sponsor | ☐

## Information Flow
00 — Master PMO Documentation Framework ¦ Information Flow Matrix (row feeds column)
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
From | Artefact ↓ feeds → | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
01 | Project Charter | bar: 01 to 04; 06; 08; 10; 13; 15; 18; 25
02 | Integrated Project Management Plan | bar: 02; 12; 19 to 25
03 | Scope Management Plan | bar: 02 to 05; 17
04 | Requirements & RTM | bar: 04 to 05; 17; 22; 25
05 | WBS & WBS Dictionary | bar: 05; 07; 09; 13 to 14; 16
06 | Schedule Management Plan | bar: 02; 06 to 07; 22
07 | Master Schedule | bar: 07; 09; 13; 22; 25
08 | Financial Management Plan | bar: 02; 08 to 09; 18; 22
09 | Project Budget | bar: 09; 22; 25
10 | Stakeholder Register | bar: 04; 10 to 12; 14; 16
11 | Stakeholder Engagement Plan | bar: 02; 11 to 12; 22
12 | Communication Plan | bar: 02; 12; 22
13 | Resource Management Plan | bar: 02; 07; 09; 13 to 14
14 | RACI Matrix | bar: 02; 12 to 14
15 | Risk Management Plan | bar: 02; 08 to 09; 15 to 16
16 | Risk Register + 5×5 Matrix | bar: 07; 09; 16; 19; 22 to 24
17 | Quality Management Plan | bar: 02; 17; 24 to 25
18 | Procurement Plan | bar: 02; 07; 09; 16; 18
19 | RAID Log | bar: 19 to 20; 22 to 24
20 | Change Request | bar: 20 to 21; 23
21 | Change Log | bar: 21 to 22; 25
22 | Project Status Report | bar: 22 to 25
23 | Decision Log | bar: 23 to 25
24 | Lessons Learned Register | bar: 24 to 25
25 | Project Closure Report | bar: 25

## Baseline & Change Control
00 — Master PMO Documentation Framework ¦ Baseline & Change-Control Relationships
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
Control category | Versioning & change rule | Artefacts
Authorizing document | Approved once at G1. Changes to objectives, budget envelope or PM authority require a Sponsor-approved CR and a major version. | 01
Baseline component | Frozen at G2 as part of the performance measurement baseline. Changed only through an approved CR; re-issue as a major version (2.0, 3.0...). | 05, 07, 09
Controlled management plan | Approved at G2 with the Integrated PMP. Minor edits = 1.x (PM); changes to process, thresholds or authority = major version via CR. | 02, 03, 06, 08, 11, 12, 13, 15, 17, 18
Living register / log | Not baselined. Maintained continuously at the defined cadence; snapshot captured at each gate; version increments on each formal issue. | 04, 10, 14, 16, 19, 21, 23, 24
Control form / record | One instance per event (e.g. per change). Each instance is uniquely identified and filed; template itself is version-controlled by the PMO. | 20
Performance report | Issued per reporting period; not baselined; each issue is a new numbered report and is never edited after distribution. | 22
Closing record | Approved at G5; becomes a permanent organizational process asset. | 25
Performance measurement baseline (PMB)
Baseline | Composition | Artefacts
Scope baseline | Approved scope statement + WBS + WBS Dictionary | 03, 05
Schedule baseline | Approved start/finish dates of activities and milestones | 07
Cost baseline | Time-phased budget incl. contingency, excl. management reserve | 09
PMB | Integrated scope-schedule-cost baseline used for EVM | 05, 07, 09
Versioning scheme
Version | Meaning | Rule
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).

## Authority & Escalation
00 — Master PMO Documentation Framework ¦ Delegated Authority, Escalation & RAG Thresholds
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
Decision | Project Manager | Change Control Board | Sponsor / Steering Committee
Scope change | None (no scope change) | Minor change within objectives | Change to objectives or major deliverables
Schedule change | ≤ 5 working days, no milestone impact | ≤ 20 working days, no gate date change | > 20 working days or any gate date change
Cost change | ≤ CAD 10,000 within control account | ≤ CAD 50,000 | > CAD 50,000 or use of management reserve
Contingency reserve | Release per risk response, logged | Release > 25% of remaining contingency | Replenishment from management reserve
Single commitment / PO | ≤ CAD 10,000 | — | ≤ CAD 100,000 (Sponsor); above: Steering Committee
Baseline (re-baselining) | — | Recommend | Approve
Risk acceptance | Low / Medium | High | Critical
Gate approval | Prepare evidence | — | Approve (G1, G4, G5: Sponsor; G2, G3: Steering Committee)
Escalation levels
Level | Escalate to | Trigger | Response time
1 | Project Manager | Within team tolerance | 2 business days
2 | Project Sponsor | Tolerance threatened, cross-functional conflict, resource conflict | 5 business days
3 | Steering Committee | Tolerance breached (Red), strategic or multi-project impact | Next meeting or 48 h ad hoc
RAG thresholds
Dimension | Green | Amber | Red
Schedule | SPI ≥ 0.95 and no milestone slip | SPI 0.90–0.94 or slip ≤ 10 wd | SPI < 0.90 or slip > 10 wd
Cost | CPI ≥ 0.95 | CPI 0.90–0.94 | CPI < 0.90 or EAC > BAC + 10%
Scope | No unapproved change | CRs pending > 2 weeks | Unapproved scope change found
Risk | No open Critical risks | Critical risk with approved response | Critical risk without response
Quality | All acceptance criteria met | Minor non-conformances open | Major non-conformance open

## Standards & Glossary
00 — Master PMO Documentation Framework ¦ Document-Control Standard & Terminology
[Project Name] • PRJ-2026-001-MDF • v0.1 Draft • Internal
Element | Standard
Document ID | <Project ID>-<Code>, e.g. PRJ-2026-001-CHR
File name | NN — Artefact Name_vX.Y.ext
Cover / metadata | Organization, project name & ID, document ID, version, status, date, sponsor, PM, approver, classification
Document control table | ID, title, project, version, status, owner, approver, classification, location, next review
Revision history | Version, date, author, description, Change Request reference
Approval block | Role, name, signature, date, decision — required for v1.0 and every major version
Header / footer | Project, title, Document ID, version / organization, classification, page x of y
Status lifecycle | Draft → In Review → Approved → Baselined → Superseded → Archived
Classification | Public / Internal / Confidential / Restricted
Predictive governance terminology
Term | Definition
Baseline | Approved version of scope, schedule or cost, changeable only through integrated change control.
BAC | Budget at Completion - total planned value of the work (cost baseline).
CCB | Change Control Board - body authorized to approve or reject change requests.
Contingency Reserve | Budget/time within the baseline for identified risks (known-unknowns); controlled by the PM.
Control Account | Management control point where scope, budget, actual cost and schedule are integrated and compared to earned value.
CPI / SPI | Cost / Schedule Performance Index (EV/AC and EV/PV). >1.00 is favourable.
Deliverable | Any unique, verifiable product, result or capability required to complete the project.
EAC / ETC | Estimate at Completion / Estimate to Complete.
EV / PV / AC | Earned Value / Planned Value / Actual Cost.
Focus Area | PMBOK 8 grouping of processes by timing: Initiating, Planning, Executing, Monitoring & Controlling, Closing.
Issue | A current condition or situation that may affect project objectives (a risk that has materialized).
Management Reserve | Budget outside the cost baseline for unknown-unknowns; released only by the Sponsor.
Performance Domain | PMBOK 8 area of practice: Governance, Scope, Schedule, Finance, Stakeholders, Resources, Risk.
Planning Package | WBS component below a control account with known content but no detailed activities yet.
RACI | Responsible, Accountable, Consulted, Informed. Exactly one 'A' per activity.
RAG | Red / Amber / Green status indicator, thresholds defined in the Integrated PMP.
Risk | An uncertain event or condition that, if it occurs, has a positive (opportunity) or negative (threat) effect on objectives.
RTM | Requirements Traceability Matrix - links each requirement to its source, WBS, deliverable and test.
Tailoring | Deliberate adaptation of approach, governance and processes to suit the project context.
WBS | Work Breakdown Structure - hierarchical decomposition of the total scope of work.
Work Package | Lowest level of the WBS for which cost and duration are estimated and managed.

## Lists (hidden)
Cls
M
C
O