[ORGANIZATION NAME]

DOCUMENT 02

Integrated Project Management Plan

[Project Name]

Integrates all subsidiary plans and baselines and defines how the project will be executed, monitored and controlled, and closed.

| Project name | [Project Name] |
| --- | --- |
| Project ID | PRJ-2026-001 |
| Document ID | PRJ-2026-001-PMP |
| Version | 0.1 |
| Status | Draft |
| Date | 2026-10-27 |
| Project Sponsor | [Project Sponsor] |
| Project Manager | [Project Manager] |
| Approver | Sponsor |
| Classification | Internal |

PMI Predictive Project Management Toolkit  •  Aligned to the PMBOK® Guide – Eighth Edition

PMBOK 8 alignment — Performance domain(s): Governance  |  Focus area(s): Planning, Monitoring & Controlling

# Document Control

| Document ID | PRJ-2026-001-PMP |
| --- | --- |
| Document title | Integrated Project Management Plan |
| Project / ID | [Project Name] / PRJ-2026-001 |
| Current version | 0.1 |
| Status | Draft |
| Owner / Author | [Project Manager] |
| Approver | Sponsor |
| Classification | Internal |
| File location | [SharePoint / repository path] |
| Next review date | [yyyy-mm-dd] |

## Revision History

| Version | Date | Author | Description of change | CR ref. |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A |

## Review & Approval

| Role | Name | Signature | Date | Decision |
| --- | --- | --- | --- | --- |
| Project Sponsor | [Project Sponsor] |  |  | Approve / Reject |
| Project Manager | [Project Manager] |  |  | Submitted |
| [Reviewer role] |  |  |  | Reviewed |

## Distribution

| Name / Group | Role | Purpose (Action / Information) |
| --- | --- | --- |
| Steering Committee | Governance | Information |
| Core project team | Delivery | Action |

Versioning: 0.x = draft; 1.0 = first approved baseline; 1.x = minor (no baseline impact); 2.0+ = major (requires an approved Change Request, doc 20).

# Contents

Right-click and choose ‘Update Field’ to build the table of contents.

# 1. Introduction

This Integrated Project Management Plan (PMP) is the authoritative source for how the project is managed. It consolidates the subsidiary plans and baselines listed in Section 6 and is maintained under change control.

# 2. Project Summary

| Project name / ID | [Project Name] / PRJ-2026-001 |
| --- | --- |
| Charter reference | PRJ-2026-001-CHR |
| Sponsor | [Project Sponsor] |
| Project Manager | [Project Manager] |
| Planned start / finish | 2026-11-02 / 2027-10-29 |
| Approved budget (BAC) | [CAD 0.00] |
| Delivery approach | Predictive (plan-driven) |

# 3. Life Cycle, Phases & Governance Gates

| Phase | Key outputs | Gate | Gate approver | Exit criteria |
| --- | --- | --- | --- | --- |
| Initiation | Charter, Stakeholder Register | G1 | Sponsor | Charter signed |
| Planning | Baselined PMP, WBS, schedule, budget, risk register | G2 | Steering Committee | PMP v1.0 approved |
| Execution | Deliverables, status reports | G3 | Steering Committee | Deliverables built & tested |
| Acceptance & Transition | Acceptance certificates, handover | G4 | Sponsor / Business owner | Formal acceptance |
| Closure | Closure Report, lessons learned, archive | G5 | Sponsor | Closure Report approved |

# 4. Tailoring Decisions

Guidance: PMBOK 8 is non-prescriptive. Record what was adopted, adapted or omitted for each performance domain and why.

| Performance domain | Tailoring decision | Rationale |
| --- | --- | --- |
| Governance | [Adopted / adapted / combined into this plan] | [Why] |
| Scope | [Adopted / adapted / combined into this plan] | [Why] |
| Schedule | [Adopted / adapted / combined into this plan] | [Why] |
| Finance | [Adopted / adapted / combined into this plan] | [Why] |
| Stakeholders | [Adopted / adapted / combined into this plan] | [Why] |
| Resources | [Adopted / adapted / combined into this plan] | [Why] |
| Risk | [Adopted / adapted / combined into this plan] | [Why] |

# 5. Governance Structure

| Body / role | Responsibilities | Meets | Decision rights |
| --- | --- | --- | --- |
| Steering Committee | Strategic direction, gate approvals, tolerance breaches | Monthly | Baseline changes > PM tolerance |
| Project Sponsor | Champions project, owns business case, releases management reserve | Bi-weekly | Scope/priority trade-offs |
| Change Control Board | Reviews and decides change requests | As needed / bi-weekly | Per thresholds in §8 |
| Project Manager | Plans, leads and controls day-to-day delivery | Daily | Within delegated tolerances |
| PMO | Standards, assurance, portfolio reporting | Monthly | Advisory |

# 6. Subsidiary Plans, Baselines & Registers

| # | Component | Document ID | Performance domain |
| --- | --- | --- | --- |
| 03 | Scope Management Plan | PRJ-2026-001-SCP | Scope |
| 04 | Requirements & RTM | PRJ-2026-001-RTM | Scope |
| 05 | WBS & WBS Dictionary | PRJ-2026-001-WBS | Scope |
| 06 | Schedule Management Plan | PRJ-2026-001-SMP | Schedule |
| 07 | Master Schedule | PRJ-2026-001-MSC | Schedule |
| 08 | Financial Management Plan | PRJ-2026-001-FMP | Finance |
| 09 | Project Budget | PRJ-2026-001-BUD | Finance |
| 10 | Stakeholder Register | PRJ-2026-001-SHR | Stakeholders |
| 11 | Stakeholder Engagement Plan | PRJ-2026-001-SEP | Stakeholders |
| 12 | Communication Plan | PRJ-2026-001-COM | Stakeholders |
| 13 | Resource Management Plan | PRJ-2026-001-RMP | Resources |
| 14 | RACI Matrix | PRJ-2026-001-RACI | Resources, Governance |
| 15 | Risk Management Plan | PRJ-2026-001-RKP | Risk |
| 16 | Risk Register + 5×5 Matrix | PRJ-2026-001-RKR | Risk |
| 17 | Quality Management Plan | PRJ-2026-001-QMP | Scope, Governance |
| 18 | Procurement Plan | PRJ-2026-001-PRC | Resources, Finance |
| 19 | RAID Log | PRJ-2026-001-RAID | Risk, Governance |
| 20 | Change Request | PRJ-2026-001-CR | Governance |
| 21 | Change Log | PRJ-2026-001-CHL | Governance |
| 22 | Project Status Report | PRJ-2026-001-PSR | Governance, Stakeholders |
| 23 | Decision Log | PRJ-2026-001-DCL | Governance |
| 24 | Lessons Learned Register | PRJ-2026-001-LLR | Governance |
| 25 | Project Closure Report | PRJ-2026-001-PCR | Governance, Finance |

## Baselines

| Baseline | Composition | Source document | Version |
| --- | --- | --- | --- |
| Scope baseline | Scope statement + WBS + WBS Dictionary | 03, 05 | 1.0 |
| Schedule baseline | Approved start/finish dates of activities & milestones | 07 | 1.0 |
| Cost baseline | Time-phased budget excluding management reserve | 09 | 1.0 |
| Performance measurement baseline | Integrated scope-schedule-cost baseline for EVM | 05, 07, 09 | 1.0 |

# 7. Integrated Change Control

| Step | Activity | Responsible | Artefact |
| --- | --- | --- | --- |
| 1 | Raise change request | Any stakeholder | 20 Change Request |
| 2 | Log and assign ID | Project Manager | 21 Change Log |
| 3 | Impact analysis (scope, schedule, cost, quality, risk, resources) | PM + SMEs | 20 |
| 4 | Decide per authority thresholds | PM / CCB / Steering Committee | 23 Decision Log |
| 5 | Update baselines & plans; re-version documents (major version) | Project Manager | Affected docs |
| 6 | Communicate decision and implement | Project Manager | 12 Communication Plan |

| Change impact | Approval authority |
| --- | --- |
| Schedule ≤ [5] days and cost ≤ CAD [10,000], no scope change | Project Manager |
| Schedule ≤ [20] days or cost ≤ CAD [50,000] or minor scope change | Change Control Board |
| Above CCB limits, milestone/gate date change, or change to objectives | Steering Committee / Sponsor |

# 8. Configuration & Document Management

Repository: [SharePoint / Confluence path]; single controlled copy per artefact.

Versioning per toolkit scheme (0.x draft, 1.0 baseline, 1.x minor, 2.0+ major via approved CR).

Configuration items: [list deliverables / components under configuration control].

# 9. Performance Measurement & Reporting

| Indicator | Green | Amber | Red |
| --- | --- | --- | --- |
| Schedule (SPI / milestone slip) | SPI ≥ 0.95 / no slip | 0.90–0.94 / ≤ 10 days | < 0.90 / > 10 days |
| Cost (CPI / variance) | CPI ≥ 0.95 | 0.90–0.94 | < 0.90 |
| Scope | No unapproved change | Pending CRs > 2 weeks | Unapproved scope change |
| Risk | No critical risks open | Critical risk with plan | Critical risk without response |
| Quality | All criteria met | Minor non-conformances | Major non-conformance |

Guidance: Reporting cadence, audiences and channels are defined in the Communication Plan (doc 12); the Project Status Report (doc 22) applies these thresholds.

# 10. Issue Management & Escalation

| Level | Escalate to | Trigger | Response time |
| --- | --- | --- | --- |
| 1 | Project Manager | Issue within team tolerance | 2 business days |
| 2 | Project Sponsor | Threatens tolerance or needs cross-functional resolution | 5 business days |
| 3 | Steering Committee | Tolerance breached / strategic impact | Next meeting or ad hoc |

# 11. Knowledge Management & Lessons Learned

Lessons are captured continuously in the Lessons Learned Register (doc 24) and reviewed at each gate.

# 12. Project Closure Approach

Closure follows the exit criteria in the Charter and is documented in the Project Closure Report (doc 25).

# 13. Approval

By signing below, the approvers confirm they have reviewed this document and accept it as the baseline for the project. Subsequent baseline changes follow integrated change control.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | [Project Sponsor] |  |  |
| Project Manager | [Project Manager] |  |  |
| Steering Committee Chair | [Name] |  |  |