## Cover
[ORGANIZATION NAME]
04 — Requirements & RTM
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Scope
Project ID | PRJ-2026-001 |  | Focus area(s) | Planning, Monitoring & Controlling
Document ID | PRJ-2026-001-RTM |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | Requirements & RTM |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | Business Owner
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. Record every requirement with a unique ID (REQ-###) and a single, testable statement.
2. Trace each requirement forward to WBS (doc 05), deliverable and test case; 'Trace complete' turns Yes when all three are filled.
3. After baselining, new or changed requirements require a Change Request (doc 20).
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## Summary
04 — Requirements & RTM ¦ Summary
[Project Name] • PRJ-2026-001-RTM • v0.1 Draft • Internal
| Requirements by status |  | Requirements by priority
| Item | Count | Item | Count
| Proposed | 0 | Must | 1
| Approved | 1 | Should | 0
| In build | 0 | Could | 0
| Verified | 0 | Won't | 0
| Accepted | 0
| Deferred | 0
| Rejected | 0
| Total requirements | 1
Traceability & test coverage
| Metric | Value
| Fully traced (WBS, deliverable, test) | 1
| Traceability % | 100%
| Tests passed | 0
| Tests failed | 0
| Test pass rate (of executed) | 0%

## RTM
04 — Requirements & RTM ¦ RTM
[Project Name] • PRJ-2026-001-RTM • v0.1 Draft • Internal
Req ID | Requirement statement | Type | Source / stakeholder | Business objective (Charter ref.) | Priority (MoSCoW) | Acceptance criteria | WBS ID | Deliverable | Design / spec ref. | Test case ID | Test status | Owner | Requirement status | Date raised | Comments | ƒ Trace complete
REQ-001 | The system shall allow authorized users to export the monthly report to PDF. | Functional | Finance Manager | O1 | Must | Export completes < 10 s; PDF matches on-screen layout | 3.2.1 | Reporting module | SPEC-04 | TC-012 | Not run | [BA] | Approved | 2026-10-20 |  | Yes

## Lists (hidden)
ReqType | MoSCoW | TestStatus | ReqStatus
Business | Must | Not run | Proposed
Stakeholder | Should | Pass | Approved
Functional | Could | Fail | In build
Non-functional | Won't | Blocked | Verified
Transition |  | N/A | Accepted
Project |  |  | Deferred
Regulatory |  |  | Rejected