[ORGANIZATION NAME]

DOCUMENT 06

Schedule Management Plan

[Project Name]

Establishes the criteria and activities for developing, monitoring and controlling the project schedule.

| Project name | [Project Name] |
| --- | --- |
| Project ID | PRJ-2026-001 |
| Document ID | PRJ-2026-001-SMP |
| Version | 0.1 |
| Status | Draft |
| Date | 2026-10-27 |
| Project Sponsor | [Project Sponsor] |
| Project Manager | [Project Manager] |
| Approver | Sponsor |
| Classification | Internal |

PMI Predictive Project Management Toolkit  •  Aligned to the PMBOK® Guide – Eighth Edition

PMBOK 8 alignment — Performance domain(s): Schedule  |  Focus area(s): Planning

# Document Control

| Document ID | PRJ-2026-001-SMP |
| --- | --- |
| Document title | Schedule Management Plan |
| Project / ID | [Project Name] / PRJ-2026-001 |
| Current version | 0.1 |
| Status | Draft |
| Owner / Author | [Project Manager] |
| Approver | Sponsor |
| Classification | Internal |
| File location | [SharePoint / repository path] |
| Next review date | [yyyy-mm-dd] |

## Revision History

| Version | Date | Author | Description of change | CR ref. |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A |

## Review & Approval

| Role | Name | Signature | Date | Decision |
| --- | --- | --- | --- | --- |
| Project Sponsor | [Project Sponsor] |  |  | Approve / Reject |
| Project Manager | [Project Manager] |  |  | Submitted |
| [Reviewer role] |  |  |  | Reviewed |

## Distribution

| Name / Group | Role | Purpose (Action / Information) |
| --- | --- | --- |
| Steering Committee | Governance | Information |
| Core project team | Delivery | Action |

Versioning: 0.x = draft; 1.0 = first approved baseline; 1.x = minor (no baseline impact); 2.0+ = major (requires an approved Change Request, doc 20).

# Contents

Right-click and choose ‘Update Field’ to build the table of contents.

# 1. Scheduling Methodology & Tool

| Methodology | Critical Path Method (CPM) with resource levelling as needed |
| --- | --- |
| Tool | [MS Project / Primavera P6 / Smartsheet]; summary maintained in Master Schedule (doc 07) |
| Calendar | [5-day week, 8 h/day, statutory holidays per province/state] |
| Units of measure | Duration in working days; effort in hours |
| Level of accuracy | Activity durations rounded to 0.5 day; ROM ±50% at initiation, ±10% at baseline |

# 2. Schedule Development

| Step | Description | Output |
| --- | --- | --- |
| Define activities | Decompose work packages (doc 05) into activities | Activity list |
| Sequence | Logical dependencies (FS, SS, FF, SF), leads/lags; no open ends | Network diagram |
| Estimate durations | Analogous, parametric, three-point (PERT: (O+4M+P)/6), expert judgement | Duration estimates |
| Develop schedule | CPM, resource levelling, schedule compression (crashing/fast-tracking) | Schedule model |
| Baseline | Approved at Gate 2 as part of PMP v1.0 | Schedule baseline |

# 3. Schedule Quality Rules

Every activity has at least one predecessor and successor (except start/finish milestones).

No activity longer than [20] working days without decomposition.

Hard constraints are minimized and justified; negative float is reported immediately.

Milestones have zero duration and are linked to gates and deliverables.

# 4. Progress Measurement Rules

| Rule | When used | Credit |
| --- | --- | --- |
| 0 / 100 | Activities ≤ 1 reporting period | 100% at finish |
| 50 / 50 | Activities spanning 2 periods | 50% at start, 50% at finish |
| Weighted milestones | Long work packages | Per agreed milestone weights |
| Physical % complete | Measurable units (e.g. units installed) | Units done / total |

# 5. Monitoring & Control

| Item | Approach |
| --- | --- |
| Status date / update cycle | [Weekly every Friday]; owners report actual start/finish and remaining duration |
| Critical path & float | Reviewed weekly; activities with float ≤ [5] days flagged as near-critical |
| Variance thresholds | Milestone slip > [5] days = Amber; > [10] days or SPI < 0.90 = Red |
| Corrective actions | Re-sequencing, resource reallocation, fast-tracking, crashing, scope trade-offs |
| Re-baselining | Only via approved Change Request; new major version of docs 07 and 02 |

# 6. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager | Owns schedule model, baseline, critical path analysis, reporting |
| Scheduler / PMO | Maintains tool, quality checks, schedule health metrics |
| Work package owners | Provide estimates and weekly progress |
| Sponsor / Steering Committee | Approve baseline and changes beyond PM tolerance |

# 7. Schedule Reporting

Milestone tracker, Gantt view and SPI are reported in the Project Status Report (doc 22) per the Communication Plan (doc 12).

# 8. Approval

By signing below, the approvers confirm they have reviewed this document and accept it as the baseline for the project. Subsequent baseline changes follow integrated change control.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | [Project Sponsor] |  |  |
| Project Manager | [Project Manager] |  |  |