## Cover
[ORGANIZATION NAME]
07 — Master Schedule
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Schedule
Project ID | PRJ-2026-001 |  | Focus area(s) | Planning, Monitoring & Controlling
Document ID | PRJ-2026-001-MSC |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | Master Schedule |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | Project Manager
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. Enter the project start date in cell C3 of the Schedule sheet; the weekly Gantt grid is built from it.
2. Enter Start and Duration (working days); Finish is calculated with WORKDAY. Baseline dates are frozen at Gate 2 and only changed via an approved Change Request.
3. Finish variance (working days) compares forecast Finish to Baseline Finish: positive = late. Milestones have duration 0.
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## Milestones
07 — Master Schedule ¦ Milestone Tracker
[Project Name] • PRJ-2026-001-MSC • v0.1 Draft • Internal
Milestone | Gate | Baseline | Forecast / actual | Variance (wd) | Status | Owner | Comment
Charter approved (Gate 1) | G1 | 2026-11-02 | 2026-11-02 | 0 | Not started | Sponsor
PMP baselined (Gate 2) | G2 | 2026-12-01 | 2026-12-01 | 0 | Not started | Steering Comm.
Final acceptance (Gate 4) | G4 | 2027-04-19 | 2027-04-19 | 0 | Not started | Business Owner
Project closure (Gate 5) | G5 | 2027-05-17 | 2027-05-17 | 0 | Not started | Sponsor

## Schedule
07 — Master Schedule ¦ Schedule
[Project Name] • PRJ-2026-001-MSC • v0.1 Draft • Internal
Project start: |  | 2026-11-02 | Status date: | 2026-10-27 | [10 empty] | Legend: |  |  | Task |  |  |  | Critical |  |  |  | Summary |  |  |  | Milestone |  |  |  | This week
ID | WBS ID | Task / milestone name | Type | Owner | Pred. | Duration (wd) | Start | ƒ Finish | Baseline start | Baseline finish | ƒ Finish var. (wd) | % complete | Status | Critical path | time axis 2026-11-02 to 2027-10-25
1 | 1 | [Project Name] | Summary | [PM] |  |  | 2026-11-02 | 2027-05-17 | 2026-11-02 | 2027-05-17 | 0 | 0% | Not started | N
2 | 1.1 | Project Management | Summary | [PM] |  |  | 2026-11-02 | 2026-12-01 | 2026-11-02 | 2026-12-01 | 0 | 0% | Not started | N
3 | 1.1.1 | Charter approved (Gate 1) | Milestone | Sponsor |  | 0 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 0 | 0% | Not started | N
4 | 1.1.2 | Develop Integrated PMP & baselines | Task | [PM] | 3 | 20 | 2026-11-03 | 2026-11-30 | 2026-11-03 | 2026-11-30 | 0 | 0% | Not started | N
5 | 1.1.2 | PMP baselined (Gate 2) | Milestone | Steering Comm. | 4 | 0 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 0 | 0% | Not started | N
6 | 1.2 | Requirements & Analysis | Summary | [BA] |  |  | 2026-11-09 | 2026-12-18 | 2026-11-09 | 2026-12-18 | 0 | 0% | Not started | N
7 | 1.2.1 | Current-state assessment | Task | [BA] | 3 | 15 | 2026-11-09 | 2026-11-27 | 2026-11-09 | 2026-11-27 | 0 | 0% | Not started | N
8 | 1.2.2 | Requirements specification | Task | [BA] | 7 | 15 | 2026-11-30 | 2026-12-18 | 2026-11-30 | 2026-12-18 | 0 | 0% | Not started | N
9 | 1.3 | Design | Summary | [Tech Lead] |  |  | 2026-12-21 | 2027-01-22 | 2026-12-21 | 2027-01-22 | 0 | 0% | Not started | N
10 | 1.3.1 | High-level design | Task | [Tech Lead] | 8 | 10 | 2026-12-21 | 2027-01-01 | 2026-12-21 | 2027-01-01 | 0 | 0% | Not started | N
11 | 1.3.2 | Detailed design | Task | [Tech Lead] | 10 | 15 | 2027-01-04 | 2027-01-22 | 2027-01-04 | 2027-01-22 | 0 | 0% | Not started | N
12 | 1.4 | Build / procure deliverables | Task | [Team] | 11 | 40 | 2027-01-25 | 2027-03-19 | 2027-01-25 | 2027-03-19 | 0 | 0% | Not started | N
13 | 1.5 | Testing & UAT | Task | [QA Lead] | 12 | 20 | 2027-03-22 | 2027-04-16 | 2027-03-22 | 2027-04-16 | 0 | 0% | Not started | N
14 | 1.5.2 | Final acceptance (Gate 4) | Milestone | Business Owner | 13 | 0 | 2027-04-19 | 2027-04-19 | 2027-04-19 | 2027-04-19 | 0 | 0% | Not started | N
15 | 1.6 | Deployment & transition | Task | [PM] | 14 | 15 | 2027-04-20 | 2027-05-10 | 2027-04-20 | 2027-05-10 | 0 | 0% | Not started | N
16 | 1.1.4 | Project closure (Gate 5) | Milestone | Sponsor | 15 | 0 | 2027-05-17 | 2027-05-17 | 2027-05-17 | 2027-05-17 | 0 | 0% | Not started | N

## Lists (hidden)
TaskType | TaskStatus | YN
Summary | Not started | Y
Task | In progress | N
Milestone | Complete
On hold
At risk