## Cover
[ORGANIZATION NAME]
12 — Communication Plan
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Stakeholders
Project ID | PRJ-2026-001 |  | Focus area(s) | Planning, Executing
Document ID | PRJ-2026-001-COM |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | Communication Plan |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | Project Manager
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. One row per communication/report/meeting. Typical predictive-project communications are pre-filled — tailor them.
2. Audience should reference stakeholder IDs or groups from the Stakeholder Register (doc 10).
3. Escalation paths and RAG thresholds come from the Integrated PMP (doc 02).
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## Escalation Path
12 — Communication Plan ¦ Escalation Path & Meeting Cadence
[Project Name] • PRJ-2026-001-COM • v0.1 Draft • Internal
Level | Escalate to | Trigger | Channel | Expected response
1 | Project Manager | Issue resolvable within team tolerance | Stand-up / direct | 2 business days
2 | Project Sponsor | Threatens tolerance, cross-functional or resource conflict | Sponsor 1:1 / email | 5 business days
3 | Steering Committee | Tolerance breached (Red) or strategic impact | SC meeting / ad hoc | Next SC or 48 h ad hoc

## Communication Plan
12 — Communication Plan ¦ Communication Plan
[Project Name] • PRJ-2026-001-COM • v0.1 Draft • Internal
ID | Communication / artefact | Purpose / objective | Audience | Key content | Method / channel | Frequency | Timing (day / time) | Owner / sender | Format / template | Feedback / approval | Storage location | Status
C-01 | Project kick-off meeting | Align team & stakeholders on objectives, scope, roles | Sponsor, team, key stakeholders | Charter, approach, roles, next steps | Meeting (in person) | Once | Week 1 | [Project Manager] | Kick-off deck | Attendance & Q&A | [Repository] | Planned
C-02 | Team stand-up / coordination | Coordinate daily work, surface blockers | Core team | Progress, plans, blockers | Meeting (virtual) | Daily | 09:00, 15 min | [Project Manager] | Action list | Verbal |  | Planned
C-03 | Weekly team status meeting | Review progress, risks, issues, actions | Core team, workstream leads | Schedule, RAID, actions | Meeting (virtual) | Weekly | Tuesday 10:00 | [Project Manager] | Agenda & minutes | Minutes circulated in 24 h | [Repository] | Planned
C-04 | Project Status Report | Report performance vs baselines | Sponsor, Steering Committee, PMO | RAG, milestones, EVM, top risks, decisions | Report | Bi-weekly | Friday | [Project Manager] | Doc 22 | Sponsor comments | [Repository] | Planned
C-05 | Steering Committee meeting | Governance, decisions, gate approvals | Steering Committee | Status, escalations, CRs, gate decisions | Meeting (in person) | Monthly | [1st Thursday] | [Project Sponsor] | SC pack | Decisions logged (doc 23) | [Repository] | Planned
C-06 | Change Control Board | Decide on change requests | CCB members | CR impact analyses | Meeting (virtual) | As needed |  | [Project Manager] | Doc 20 | CCB decision | [Repository] | Planned
C-07 | Sponsor 1:1 | Escalations, steering, relationship | Sponsor | Key issues, decisions needed | Meeting (virtual) | Bi-weekly |  | [Project Manager] | Informal | Verbal |  | Planned
C-08 | Stakeholder newsletter | Build awareness and support | Wider organization, end users | Progress, what's changing, when | Newsletter | Monthly |  | [Change lead] | Newsletter template | Survey / feedback form | [Intranet] | Planned
C-09 | Gate review | Formal phase approval | Steering Committee | Gate checklist, deliverables, readiness | Presentation | Per gate |  | [Project Manager] | Gate checklist | Signed approval | [Repository] | Planned
C-10 | Lessons learned session | Capture and share lessons | Team, key stakeholders | What worked / to improve | Workshop | Per gate |  | [Project Manager] | Doc 24 | Register updated | [Repository] | Planned
C-11 | Project closure communication | Announce completion & handover | All stakeholders | Outcomes, benefits, thanks, contacts | Email | Once | At closure | [Project Sponsor] | Doc 25 summary |  | [Repository] | Planned

## Lists (hidden)
Method | Freq | CStatus
Meeting (in person) | Once | Planned
Meeting (virtual) | Daily | Active
Email | Weekly | Retired
Report | Bi-weekly
Dashboard | Monthly
Intranet / SharePoint | Quarterly
Workshop | Per gate
Newsletter | As needed
Presentation