## Cover
[ORGANIZATION NAME]
16 — Risk Register + 5×5 Matrix
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Risk
Project ID | PRJ-2026-001 |  | Focus area(s) | Planning, Executing, Monitoring & Controlling
Document ID | PRJ-2026-001-RKR |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | Risk Register + 5×5 Matrix |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | Project Manager
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. Describe each risk with cause → event → effect ('Because of…, … may occur, resulting in…').
2. Score probability and impact 1–5 using the scales in the Risk Management Plan (doc 15). Score = P × I; rating bands: 1–4 Low, 5–9 Medium, 10–15 High, 16–25 Critical.
3. The 5×5 Matrix sheet counts open risks per cell (inherent and residual). Materialized risks move to the Issues log in the RAID Log (doc 19).
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## 5x5 Matrix
16 — Risk Register + 5×5 Matrix ¦ Probability × Impact Heat Map (open risks)
[Project Name] • PRJ-2026-001-RKR • v0.1 Draft • Internal
| INHERENT (before response) | [5 empty] | RESIDUAL (after response)
|  |  |  | IMPACT → | [5 empty] | IMPACT →
| PROB. ↓ | 1 | 2 | 3 | 4 | 5 | PROB. ↓ | 1 | 2 | 3 | 4 | 5
| 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 1 | 0 | 0
| 2 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Open risks by rating
| Rating | Inherent | Residual | Action required
| Critical | 0 | 0 | Escalate to Sponsor/SC within 24 h; weekly review
| High | 1 | 0 | Response plan within 5 days; weekly review
| Medium | 1 | 2 | Response plan; monthly review
| Low | 0 | 0 | Accept & monitor (watch list)
| Total EMV of open risks (contingency basis): |  |  |  |  | 12500

## Scales
16 — Risk Register + 5×5 Matrix ¦ Probability & Impact Scales (from doc 15)
[Project Name] • PRJ-2026-001-RKR • v0.1 Draft • Internal
Score | Probability | Cost impact | Schedule impact | Scope / quality | Safety / reputation
5 | > 80% | > 20% BAC | > 20% / misses gate | Product unusable | Serious injury / national media
4 | 61–80% | 10–20% | 10–20% | Unacceptable to sponsor | Lost-time injury / regulator
3 | 41–60% | 5–10% | 5–10% | Major areas affected | Medical aid / local media
2 | 21–40% | 1–5% | 1–5% | Minor areas affected | First aid / internal complaint
1 | ≤ 20% | < 1% | < 1% | Barely noticeable | Negligible
EMV uses probability mid-points: 1=10%, 2=30%, 3=50%, 4=70%, 5=90%. Opportunities produce negative EMV (reduce contingency).

## Risk Register
16 — Risk Register + 5×5 Matrix ¦ Risk Register
[Project Name] • PRJ-2026-001-RKR • v0.1 Draft • Internal
Risk ID | Date raised | Category (RBS) | Threat / opportunity | Cause | Risk event | Effect on objectives | Trigger / early warning | Prob. (1-5) | Impact (1-5) | ƒ Score | ƒ Rating | Proximity | Response strategy | Response actions | Risk owner | Action due | Residual P | Residual I | ƒ Residual score | ƒ Residual rating | Contingency / fallback plan | Cost impact if occurs (CAD) | ƒ EMV (P% × cost) | Status | Last reviewed
R-001 | 2026-10-20 | External | Threat | Single supplier for key component | Supplier delivers late | Build phase delayed 3–4 weeks; cost of idle team | Supplier misses interim milestone | 3 | 4 | 12 | High | 1-3 months | Mitigate | Weekly supplier check-ins; identify alternate supplier; milestone payments | [PM] | 2026-12-01 | 2 | 3 | 6 | Medium | Engage alternate supplier; re-sequence work | 40000 | 20000 | Open | 2026-10-20
R-002 | 2026-10-20 | Organizational | Opportunity | Shared platform being built by another program | Reuse of platform components | Reduce build effort by ~15% | Platform release confirmed | 2 | 3 | 6 | Medium | 3-6 months | Enhance | Agree reuse with program lead; align architecture | [Tech Lead] | 2027-01-15 | 3 | 3 | 9 | Medium |  | 25000 | -7500 | Monitoring | 2026-10-20

## Lists (hidden)
RBS | TO | Score5 | Prox | Strategy | RiskStatus
Technical | Threat | 1 | < 1 month | Avoid | Open
External | Opportunity | 2 | 1-3 months | Transfer | Monitoring
Organizational |  | 3 | 3-6 months | Mitigate | Occurred (issue)
Project management |  | 4 | > 6 months | Accept | Closed
Health, safety & environment |  | 5 |  | Escalate
Commercial / contractual |  |  |  | Exploit
Share
Enhance