## Cover
[ORGANIZATION NAME]
19 — RAID Log
[Project Name]
DOCUMENT CONTROL |  |  | PMBOK® 8 ALIGNMENT
Project name | [Project Name] |  | Performance domain(s) | Risk, Governance
Project ID | PRJ-2026-001 |  | Focus area(s) | Executing, Monitoring & Controlling
Document ID | PRJ-2026-001-RAID |  | Toolkit | PMI Predictive Project Management Toolkit
Document title | RAID Log |  | Standard | Aligned to the PMBOK® Guide – Eighth Edition
Version | 0.1
Status | Draft
Date | 2026-10-27
Project Sponsor | [Project Sponsor]
Project Manager / Owner | [Project Manager]
Approver | Project Manager
Classification | Internal
Currency | CAD
File location | [SharePoint / repository path]
REVISION HISTORY
Version | Date | Author | Description of change | CR ref. | Approved by
0.1 | 2026-10-27 | [Project Manager] | Initial draft created from toolkit template | N/A
VERSIONING SCHEME
0.1 - 0.9 | Draft | Work in progress. Increment the minor digit for each review cycle (0.1, 0.2 ...).
1.0 | Approved / Baselined | First version formally approved by the designated approver. Becomes the baseline.
1.1, 1.2 ... | Minor revision | Editorial or clarifying change with NO impact on scope, schedule or cost baselines. PM approval.
2.0, 3.0 ... | Major revision | Change that alters a baseline. Requires an approved Change Request (doc 20) logged in the Change Log (doc 21).
HOW TO USE THIS WORKBOOK
1. Four logs in one workbook: Risks (summary view — the full register is doc 16), Assumptions, Issues and Dependencies.
2. Review the RAID Log in the weekly team meeting; the Dashboard counts open items by priority and age.
3. Escalate issues per the escalation path in the Integrated PMP (doc 02) and Communication Plan (doc 12).
4. Navy column headers = input columns (shaded rows are for data entry). Teal headers marked ƒ = calculated columns — do not overwrite.
5. Drop-down lists enforce the toolkit's controlled vocabulary. Rows shown in grey italics are examples — overwrite or delete them.
6. Update the Version/Status/Date above and add a Revision History row each time the workbook is re-issued.

## Dashboard
19 — RAID Log ¦ RAID Dashboard
[Project Name] • PRJ-2026-001-RAID • v0.1 Draft • Internal
| Log | Open | In progress | On hold | Closed | Total
| Risks | 1 | 0 | 0 | 0 | 1
| Assumptions | 1 | 0 | 0 | 0 | 1
| Issues | 1 | 0 | 0 | 0 | 1
| Dependencies | 1 | 0 | 0 | 0 | 1
Open issues by priority
| Critical | 0
| High | 1
| Medium | 0
| Low | 0
| Overdue issues | 0
| Average age of open issues (d) | 7
| Red dependencies | 0

## Risks
19 — RAID Log ¦ Risks
[Project Name] • PRJ-2026-001-RAID • v0.1 Draft • Internal
Risk ID (doc 16) | Risk description | Score | ƒ Rating | Owner | Response summary | Status | Last updated
R-001 | Supplier delivers key component late | 12 | High | [PM] | Weekly check-ins; alternate supplier | Open | 2026-10-20

## Assumptions
19 — RAID Log ¦ Assumptions
[Project Name] • PRJ-2026-001-RAID • v0.1 Draft • Internal
Assumption ID | Assumption | Category | Source | Impact if false | Owner | Validate by | Validation status | Status
A-001 | Business SMEs available 4 h/week during requirements phase | Resource | Charter | Requirements delayed; schedule slip | [Business Owner] | 2026-11-20 | Not validated | Open

## Issues
19 — RAID Log ¦ Issues
[Project Name] • PRJ-2026-001-RAID • v0.1 Draft • Internal
Issue ID | Date raised | Issue description | Category | Priority | Impact | Raised by | Owner | Action / resolution | Target date | Escalation level | Status | Date closed | ƒ Age (days) | ƒ Overdue | Related risk / CR
I-001 | 2026-10-20 | Test environment not available as planned | Technical | High | Testing start at risk (5 days) | [QA Lead] | [Tech Lead] | Escalate to IT ops; use temporary environment | 2026-11-17 | 1 - PM | Open |  | 7 |  | R-003
Formulas:
ƒ Age (days) = IF([Date raised]="","",IF([Date closed]<>"",[Date closed]-[Date raised],TODAY()-[Date raised]))
ƒ Overdue = IF(OR([Target date]="",[Status]="Closed"),"",IF(TODAY()>[Target date],"Yes",""))

## Dependencies
19 — RAID Log ¦ Dependencies
[Project Name] • PRJ-2026-001-RAID • v0.1 Draft • Internal
Dependency ID | Dependency description | Type | Direction | Other party / project | Deliverable / WBS affected | Needed by | Owner | Health (RAG) | Status | Comments
D-001 | Network upgrade by IT Infrastructure project | External | Inbound (we need) | [Infra project] | 1.6.2 | 2027-04-01 | [PM] | Green | Open

## Lists (hidden)
Score25 | ItemStatus | ACat | AVal | ICat | Priority | Esc | DType | Dir | RAG
1 | Open | Resource | Not validated | Scope | Critical | 1 - PM | Internal | Inbound (we need) | Green
2 | In progress | Technical | Validated | Schedule | High | 2 - Sponsor | External | Outbound (others need) | Amber
3 | On hold | Financial | Invalid – raise risk/issue | Cost | Medium | 3 - Steering Committee | Mandatory |  | Red
4 | Closed | Schedule |  | Quality | Low |  | Discretionary
5 |  | External |  | Resource
6 |  | Business |  | Stakeholder
8 |  |  |  | Technical
9 |  |  |  | Vendor
10
12
15
16
20
25