## Slide 1
[ORGANIZATION NAME]
Project Status Report
[Project Name]
Reporting period: [yyyy-mm-dd] to [yyyy-mm-dd] • Report #[nn]
PROJECT ID
PRJ-2026-001
DOCUMENT ID
PRJ-2026-001-PSR
VERSION
0.1
STATUS
Draft
SPONSOR
[Project Sponsor]
PROJECT MANAGER
[Project Manager]
CLASSIFICATION
Internal
PMI Predictive Project Management Toolkit • Aligned to the PMBOK® Guide – Eighth Edition

## Slide 2
Executive Summary
[Project Name]
Status date: [yyyy-mm-dd]
Overall status against baselines using the RAG thresholds defined in the Integrated PMP (doc 02).
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
2
OVERALL
Green
[One-line rationale]
SCOPE
Green
No unapproved change
SCHEDULE
Amber
SPI 0.93; milestone M3 +6 wd
COST
Green
CPI 1.02
RISK
Amber
1 critical risk with plan
QUALITY
Green
All criteria met
RESOURCES
Green
Fully staffed
STAKEHOLDERS
Green
Engagement on target
Summary
[Progress this period and key achievements]
[Main concerns and corrective actions]
[Decisions or support required from the Sponsor / Steering Committee]

## Slide 3
Milestones & Schedule
[Project Name]
Status date: [yyyy-mm-dd]
Baseline vs forecast; variance in working days (positive = late). Source: Master Schedule (doc 07).
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
3
Milestone | Gate | Baseline | Forecast / actual | Var. (wd) | Status | Comment
Charter approved | G1 | [date] | [date] | 0 | Green | Complete
PMP baselined | G2 | [date] | [date] | 0 | Green | 
[Design complete] |  | [date] | [date] | +6 | Amber | [Reason / recovery]
Final acceptance | G4 | [date] | [date] | 0 | Green | 
Project closure | G5 | [date] | [date] | 0 | Green | 
SPI
[0.93]
CRITICAL PATH FLOAT
[0 d]
% COMPLETE (PLANNED / ACTUAL)
[45% / 42%]

## Slide 4
Financial & Earned Value Performance
[Project Name]
Status date: [yyyy-mm-dd]
All figures in CAD. Source: Project Budget (doc 09) — Cash Flow & EVM sheet.
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
4
BAC
[0]
EAC
[0]
CPI
[1.02]
SPI
[0.93]
VAC
[0]
Reserve used
[0%]
Metric | To date | Previous period | Threshold | Status | Commentary
Planned Value (PV) | [ ] | [ ] |  |  | 
Earned Value (EV) | [ ] | [ ] |  |  | 
Actual Cost (AC) | [ ] | [ ] |  |  | 
Cost Performance Index (CPI) | [ ] | [ ] | ≥ 0.95 | Green | 
Schedule Performance Index (SPI) | [ ] | [ ] | ≥ 0.95 | Amber | 
Estimate at Completion (EAC) | [ ] | [ ] | ≤ BAC | Green | 

## Slide 5
Top Risks & Issues
[Project Name]
Status date: [yyyy-mm-dd]
Open risks scored ≥ 10 (High/Critical) and open High/Critical issues. Sources: docs 16 and 19.
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
5
ID | Type | Description | P×I / priority | Rating | Response / action | Owner | Due
R-001 | Risk | [Supplier delivers key component late] | 3×4 = 12 | High | [Weekly check-ins; alternate supplier] | [PM] | [date]
R-00x | Risk |  |  |  |  |  | 
I-001 | Issue | [Test environment unavailable] | High |  | [Escalated to IT ops] | [Tech Lead] | [date]
I-00x | Issue |  |  |  |  |  | 
Risk profile (open risks)
CRITICAL
[n]
HIGH
[n]
MEDIUM
[n]
LOW
[n]

## Slide 6
Changes & Decisions Required
[Project Name]
Status date: [yyyy-mm-dd]
Change requests from the Change Log (doc 21); decisions recorded in the Decision Log (doc 23).
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
6
Change requests
CR ID | Title | Schedule (wd) | Cost (CAD) | Authority | Status
CR-001 | [Add mobile access to reporting module] | +8 | 18,000 | CCB | Pending decision
CR-00x |  |  |  |  | 
Decisions required from Sponsor / Steering Committee
# | Decision required | Options | Recommendation | Needed by
1 | [Decision] | [A / B] | [Recommended option] | [date]
2 |  |  |  | 

## Slide 7
Accomplishments & Next Period
[Project Name]
Status date: [yyyy-mm-dd]
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
7
Accomplished this period
• [Deliverable / milestone completed]
• [Key activity completed]
• [Stakeholder event held]
• [ ]
Planned for next period
• [Planned deliverable / activity]
• [Upcoming milestone]
• [Upcoming decision / gate]
• [ ]

## Slide 8
Appendix — Document Control & RAG Definitions
[Project Name]
Status date: [yyyy-mm-dd]
[Organization Name] • PRJ-2026-001-PSR v0.1 • Classification: Internal
8
Field | Value
Document ID | PRJ-2026-001-PSR
Project / ID | [Project Name] / PRJ-2026-001
Version / status | 0.1 / Draft
Owner | [Project Manager]
Approver | Project Manager
Classification | Internal
Distribution | Per Communication Plan (doc 12)
Version | Date | Author | Change
0.1 | 2026-10-27 | [Project Manager] | Initial template
RAG | Definition
Green | On track; within tolerance
Amber | At risk; tolerance threatened; PM corrective action
Red | Tolerance breached; escalation to Sponsor / Steering Committee